ЗАЯВКА НА ФИНАНСИРОВАНИЕ ГУМАНИТАРНОГО ПРОЕКТА  ГОСУДАРСТВЕННОГО УЧРЕЖДЕНИЯ «ЧАШНИКСКИЙ ИСТОРИЧЕСКИЙ МУЗЕЙ»

| 1. | Наименование проекта | «Знаменитый человек Чашникского края – Жорес Алфёров» |
| --- | --- | --- |
| 2. | Наименование организации | Государственное учреждение «Чашникский исторический музей» |
| 3. | Физический и юридический адрес организации, телефон, факс, e-mail | 211149 Республика Беларусь, Витебская область, г. Чашники, ул. Советская, д.71 тел. 8 02133 6 30 81 е-mail: chashnikiistmysej@chashnikimusey.by |
| 4. | Информация об организации | Государственное учреждение «Чашникский исторический музей» Музей создан в августе 1987 г. решением Бюро ЦК КПБ. Открыт для посетителей в марте 1991 г, 30 июня 2006 года решением № 469 Витебского облисполкома зарегистрирован как ГУ "Чашникский исторический музей". С 2019 года музей переехал в большое трехэтажное здание по улице Советская д.71. Расширение площади позволило открыть новые экспозиции, в том числе отражающие не только историю, но и современность Чашникской земли. Выставочная площадь увеличилась с 254,10 кв. м до 429 кв.м. В июле 2020 года состоялось открытие экспозиций: «Великая Отечественная война глазами мирных жителей», «Род Володковичей на Чашниччине», «Экономический потенциал Чашниччины. Промышленность», «Лесное и сельское хозяйство Чашниччины», «Культура Чашниччины», «Развитие образования на Чашниччине», «Достойный сын народа своего». Музей сегодня: это малый храм культуры в городе; это музейный фонд в более 10 000 предметов; это с любовью оформленные экспозиции, выставки; это вечера-встречи, музейные уроки, экскурсии, игровые программы, и многое другое; это место, где никогда и никому не отказывают в проведении мероприятия и всегда рады помочь и предоставить помещение; это место, где по всем интересующим Вас вопросам дадут грамотную консультацию и доброжелательный совет. У посетителей музея есть возможность познакомиться с уникальными предметами, среди которых: предметы искусства, нумизматики, коллекции печатных изданий, документов, богатейший этнографический материал. |
| 5. | Руководитель организации Менеджер проекта | Иванова Наталья Вячеславовна, директор тел. 8 02133 6 30 81 е-mail: hashnikiistmysej@chashnikimusey.by Cтарший научный сотрудник тел. 8 02133 6 30 81 е-mail: chashnikiistmysej@chashnikimusey.by |
| 6. | Целевая аудитория | Жители и гости Чашникского района |
| 7. | Прежняя помощь, полученная от других иностранных источников | Опыта сотрудничества с иностранными партнерами не имеем |
| 8. | Требуемая сумма | 105 480 $ (36 000 бел.руб.) |
| 9. | Софинансирование | Внебюджетные ресурсы |
| 10. | Срок проекта | 2026-2028 |
| 11. | Цель проекта | Создание условий, способствующих патриотическому, духовному развитию молодого поколения, вовлечения в процесс передачи, сохранения преемственности поколений и формирование уважения к истории своей страны, начинающегося со знания истории своей местности. |
| 12. | Задачи проекта | - Заказ исполнения бюста и постамента (эскиз) - Заказ исполнения бюста и постамента в материале - Доставка и монтаж бюста и постамента на месте установки в городском сквере - Благоустройство прилегающей территории - Торжественное открытие памятника - Создание в музее экспозиции, посвящённой Ж.И. Алферову. - Включить сведения о Ж.И. Алферове в материал экскурсии по экспозиции « » , пешеходную экскурсию по городу. - Выпустить серию информационных буклетов с целью популяризации деятельности Ж. Алферова |
| 13. | Детальное описание деятельности в рамках проекта в соответствии с поставленными задачами | Задача 1. Заказ исполнения бюста и постамента (эскиз): 1.1 Разработка эскизного проекта; 1.2. Проведение конкурса эскизных проектов памятника-бюста Ж.И. Алферову; 1.3. Отбор конкурсных работ эскизных проектов памятника-бюста Ж.И. Алферову; Задача 2. Заказ исполнения бюста и постамента в материале (натуре): 2.1. Выполнение рабочей модели (рабочего эскиза); 2.2. Выполнение модели (картона) в натуральную величину; 2.3. Изготовление памятника-бюста в материале (натуре). Задача 3. Доставка и монтаж бюста и постамента на месте установки в городском сквере: 3.1. Подготовка по установке (монтажу) проектных и строительных работ и услуг, связанные с проектированием, строительно-монтажными работами по созданию пьедестала и установке монументальной скульптуры. 3.2. Выполнение проектных и строительных работ, связанных с установкой (монтажом) произведения искусства. 3.3. Рытье котлована под фундамент по размеру основания, глубиной 100 см; 3.4. Заливка бетоном; 3.5. Установка бордюров; 3.6. Укладывание плитки; 3.7. Разметка места установки постамента, по размеру основания; 3.8. С использованием манипулятора, устанавливается постамент по центру площадки; 3.9. Приподняв манипулятором постамент, на место установки наносится клей и устанавливается постамент; 3.10. С помощью манипулятора устанавливают бюст на постамент по центру; 3.11. Прокраска стыковочных швов. Задача 4. Благоустройство прилегающей территории: 4.1. разработка проекта озеленения территории; 4.2. оформление проекта в виде плана, рисунков, презентации; 4.3. предложить проект для утверждения и реализации руководству; 4.4. приобретение саженцев деревьев и кустарников, семян цветов и газонной травы; 4.5. посадка саженцев деревьев и кустарников, семян цветов и газонной травы; 4.6. приобретение и установка скамеек, приобретение краски и покраска скамеек; 4.7. приобретение и укладка тротуарной плитки для дорожек. Задача 5. Торжественное открытие памятника: 5.1. Приглашение гостей и жителей города; 5.2. Подготовка сценария. Задача 6. Создание в музее экспозиции, посвящённой Ж.И. Алферову: 6.1. Приобретение мебели для оформления экспозиции; 6.2. поиск и размещение текстовых, фото и других материалов о жизни и деятельности Ж.И. Алферова; 6.3. Оформление экспозиции. Задача 7. Включить сведения о Ж.И. Алферове в материал экскурсии по экспозиции «Наша Чашниччина», пешеходную экскурсию по городу. 7.1. Поиск и систематизация сведений о Ж.И. Алферове; 7.2. добавление сведений и редактирование текста экскурсий. Задача 8. Издание серии информационных буклетов с целью популяризации деятельности Ж. Алферова. 8.1. Изучение и отбор материалов для включения в буклет; 8.2. Разработка макета буклета; 8.3. Печать буклета. |
| 14. | Обоснование проекта | Время выдвигает своих героев. Это не обязательно герои военных действий. В мирное время героями можно назвать людей, которые оставляют после себя, а может и при жизни, что-то важное, то, благодаря чему их будут помнить потомки. Знание истории малой родины, знание и память о своих земляках, их делах – долг каждого. Издревле водится так, что русский человек, русская душа, будучи вдали от своей Родины, от своего места проживания, нескрываемо радуется при встрече земляка. Что означает это слово, которое вмиг роднит чужих людей. Обратимся к словарю Ожегова: «Земляк – уроженец одной с кем-нибудь местности». «Землячество – принадлежность по рождению к одной местности; объединение уроженцев одной местности». Толковый словарь русского языка. В толковом словаре русского языка С.И. Ожегова, Н.Ю. Шведова дается такое объяснение слова «земляк»: ЗЕМЛЯ́К, -а, м. Уроженец одной с кем-н. местности. Мы с ним ~и. В словаре русских синонимов близкими по значению к слову «земляк» являются слова: единоплеменник, товарищ; соземец, соотечественник, своеземец, зема, земеля, единоземец, землячок. В данном проекте хочется рассказать о своем земляке, о беззаветном труженике, человеке, которым гордится мои город, а также о человеке не являющемся земляком, но внёсшим большой вклад в историю моего города, страны. Мотивом выбранной темы послужил не только интерес и уважение к жизни и деятельности Жореса Ивановича Алферова, но и хотелось подробнее узнать историю его жизни, профессиональные победы и достижения. Имя Жореса Алфёрова на слуху во всем мире, но по-особенному к нему относятся на родине. Ведь свои первые шаги по дороге жизни знаменитый физик Жорес Иванович сделал на нашей земле. Здесь его корни. Жорес Иванович Алфёров родился 13 марта 1930 года в Витебске. Его отец Иван Карпович Алфёров, крестьянин родом из белорусского городка Чашники, работал портовым грузчиком. Он воевал на фронтах Первой мировой войны и дослужился до звания гусарского унтер-офицера, а в 1917 году примкнул к большевикам. Со своей женой Иван Алфёров познакомился в 1920-е гг. на пограничной заставе около местечка Крайск под Минском. Своё необычное имя будущий нобелевский лауреат получил в честь французского социалиста Жана Жореса. Семья переезжала вслед за новыми назначениями по службе Ивана Карповича, который после выхода в запас работал директором различных комбинатов целлюлозной и деревообрабатывающей промышленности. Алфёровы жили в Сталинграде, в Сибири, на Урале, в Белоруссии, поэтому Жорес нередко менял школы. Мужскую среднюю школу № 42 в Минске будущий знаменитый физик в 1947 году окончил с золотой медалью. Год проучился в Белорусском политехническом институте, затем поступил на второй курс Ленинградского электротехнического института. В 1953-м начал работать в Физико-техническом институте, в 1987-м возглавил его. В 1961 году защитил ученую степень кандидата, в 1970-м — доктора физико-математических наук. Еще через два года он стал профессором. На счету ученого множество высоких карьерных ступеней. С 1991-го по 2017-й он являлся вице-президентом Российской академии наук, кроме того, в 1995-м был избран иностранным членом НАН Беларуси. Жорес Алфёров — автор более 500 научных работ и 50 изобретений. Исследования в области физики полупроводников, полупроводниковой и квантовой электроники и технической физики принесли ему славу ученого-первооткрывателя и положили начало новой научной школе — физике полупроводниковых гетероструктур. Первые в СССР транзисторы, фотодиоды, германиевые выпрямители — ко всему этому приложил руку Жорес Алфёров. Недаром еще в 1972 году ученый был удостоен Ленинской премии — самой высокой награды Союза за достижения в области науки. Перечисление всех высоких наград и регалий научного светила, общественного и политического деятеля заняло бы несколько страниц. Разработанные им солнечные батареи обеспечивали электричеством космическую станцию «Мир». Не потому ли его имя увековечено и в космосе? В честь Жореса Алфёрова в 1997 году был назван астероид 3884, а в 2021-м — крупнейший из найденных якутский алмаз весом более 70 карат. Жоресу Алфёрову и Герберту Кремеру совместно за разработку полупроводниковых гетероструктур, используемых в высокоскоростной и оптоэлектронике, была присуждена половина Нобелевской премии по физике 2000 года. Значительную часть собственного вознаграждения нобелевский лауреат потратил на создание Международного Алфёровского фонда поддержки образования и науки. Далее пополнял его за счет своих премий и гонораров. Целью фонда являлась поддержка научных исследований молодых ученых, содействие проведению научно-исследовательских работ. В числе стипендиатов фонда были студенты ВГТУ, почетным профессором которого знаменитый ученый являлся с 2007 года, и учащиеся Витебской гимназии № 1, с 2019 года носящей имя Жореса Алфёрова. Здесь сложилась традиция в ознаменование дня рождения великого ученого — 15 марта — проводить Алферовские чтения. Именитый физик постоянно с удовольствием приезжал в Беларусь и на малую родину в частности, встречался и беседовал с земляками. |
| 15. | Деятельность после окончания проекта | После окончание проекта в выставочном зале музее «Наша Чашниччина» будет создана экспозиции, посвящённой Ж.И. Алферову, сведения о Ж.И. Алферове будет внесен материал в обзорную экскурсию музея, использоваться при пешеходной экскурсии по городу. |
| 16. | Бюджет проекта | Изготовление бронзовой таблички на белорусском языке размером 45х45 см. – 300 бел. руб. Изготовление гранитного постамента 165х40см. – 1200 руб. Изготовление памятника-бюста 70 см. – 3500 бел. руб. в стоимость входит -лепка скульптором с фото; -формовка; -отливка; -шлифовка; - патина (по желанию) Земляные работы: устройство песчаного основания под фундамент, песок для строительных работ, устройство щебёночного основания под фундамент – 3000 бел. руб. Монтаж фундамента – 1500 бел.руб. Установка памятника-бюста – 1500 бел. руб. Установка постамента на фундамент – 1500 руб. Благоустройство места установки памятника-бюста – 8000 бел. руб. Укладка тротуарной плитки вокруг памятника-бюста – 6 000 бел. руб. В стоимость входит монолитный армированный фундамент + облицовка и укладка гранитной плитки (2,0*2,3 m) Материалы: песок, цемент, клей плиточный, щебень – 2500 бел. руб. Заработная плата рабочих – 7000 бел. руб. ИТОГО: 36 000 бел. руб. 105 480 $ |

Будем рады сотрудничеству!

APPLICATION FOR FUNDING OF THE HUMANITARIAN PROJECT OF THE STATE INSTITUTION "CHASHNIK HISTORICAL MUSEUM"

| 1. | Name of the project | "Famous person of the Chashnik region-Zhores Alferov" |
| --- | --- | --- |
| 2. | Organization name | State Institution "Chashnik Historical Museum" |
| 3. | Physical and legal address of the organization, phone, fax, e - mail | 211149 Republic of Belarus, Vitebsk region, Chashniki, Sovetskaya str., 71 tel. 8 02133 6 30 81 e-mail: chashnikiistmysej@chashnikimusey.by |
| 4. | Information about the organization | State Institution "Chashnik Historical Museum" The museum was established in August 1987 by the decision of Bureau of the Central Committee of the CPB. Opened to the public in March 1991, on June 30, 2006, by decision No. 469 of the Vitebsk Regional Executive Committee, it was registered as the State Institution "Chashnik Historical Museum". Since 2019, the museum has moved to a large three-story building at Советская71 Sovetskaya Street. The expansion of the square allowed opening new expositions, including those reflecting not only the history, but also the modernity of the Chashnik land. The exhibition area increased from 254.10 sq. m. m to 429 sq. m. In July 2020, the following expositions were opened: "The Great Patriotic War through the eyes of civilians", "The Volodkovich Family in Chashnichchina", "The Economic Potential of Chashnichchina. Industry", "Forestry and agriculture of Chashnichchina", "Culture of Chashnichchina", "Development of education in Chashnichchina", "A worthy son of his people". Museum today: it is a small temple of culture in the city; it is a museum collection of more than 10,000 objects; it is lovingly designed expositions, exhibitions; it is evenings-meetings, museum lessons, excursions, game programs, and much more; it is a place where no one is ever denied an event and is always happy to help and provide a room; this is a place where all the questions you are interested in will give competent advice and friendly advice. Visitors to the museum have the opportunity to get acquainted with unique objects, including: objects of art, numismatics,collections of printed publications, documents, and the richest ethnographic material. |
| 5. | Head of the organization Project Manager | Natalia Ivanova, Director tel. 8 02133 6 30 81 e-mail: chashnikiistmysej@chashnikimusey.by Senior Researcher tel. 8 02133 6 30 81 e-mail: chashnikiistmysej@chashnikimusey.by |
| 6. | Target audience | Residents and guests of Chashniksky district |
| 7. | Previous assistance received from other foreign sources | We do not have any experience in cooperation with foreign partners |
| 8. | The required amount | 36 000 BYN. 105 480 $ |
| 9. | Co-financing | Budgetary resources |
| 10. | Project deadline | 2026-2028 |
| 11. | The goal of the project | Is to create conditions that promote patriotic and spiritual development of the younger generation, involve them in the process of transmission, preserve the continuity of generations and create respect for the history of their country, starting with knowledge of the history of their area. |
| 12. | Project objectives | - Order of execution of the bust and pedestal (sketch) - Ordering the execution of the bust and pedestal in the material - Delivery and installation of the bust and pedestal at the installation site in the city square - Improvement of the adjacent territory - Grand opening of the monument - Creation of an exhibition dedicated to Zh. I. Alferov in the museum. - Include information about Zh. I. Alferov in the material of the exhibition tour"", a walking tour of the city. - To issue a series of informational booklets to promote the activities of Zh. Alferova |
| 13. | Detailed description of the project activities in accordance with | The tasks set Task 1. Order of execution of the bust and pedestal (sketch): 1.1 Development of the draft design; 1.2. Holding a competition of draft designs of the monument-bust to Zh. I. Alferov; 1.3. Selection of competitive works of draft designs of the monument-bust to Zh. I. Alferov; Task 2. Ordering the execution of the bust and pedestal in the material (in kind): 2.1. Making a working model (working sketch); 2.2. Making a model (cardboard) in full size; 2.3. Making a monument-bust in the material (in kind). Task 3. Delivery and installation of the bust and pedestal at the installation site in the city square: 3.1. Preparation for the installation of design and construction works and services related to the design, construction and installation of a pedestal and installation of a monumental sculpture. 3.2. Performing design and construction works related to the installation (installation) of a work of art. 3.3. Digging a foundation pit according to the size of the base, 100 cm deep; 3.4. Pouring concrete; 3.5. Installing curbs; 3.6. Laying tiles; 3.7. Marking the place of installation of the pedestal, according to the size of the base; 3.8. Using a manipulator, the pedestal is installed in the center of the site; 3.9. By lifting the pedestal with the manipulator, glue is applied to the installation site and the pedestal is installed; 3.10. Using the manipulator, the bust is placed on the pedestal in the center; 3.11. Painting the connecting seams. Task 4. Improvement of the adjacent territory: 4.1. development of the landscaping project; 4.2. design of the project in the form of a plan, drawings, presentation; 4.3. offer the project for approval and implementation to the management; 4.4. purchase of saplings of trees and shrubs, seeds of flowers and lawn grass; 4.5. planting of saplings of trees and shrubs, seeds of flowers and lawn grass; 4.6. purchase of saplings of trees and shrubs, seeds of flowers and lawn grass; purchase and installation of benches, purchase of paint and painting of benches; 4.7. purchase and laying of paving slabs for paths. Task 5. Grand opening of the monument: 5.1. Inviting guests and residents of the city; 5.2. Preparing the script. Task 6. Creating an exhibition dedicated to Zh. I. Alferov in the museum: 6.1. Purchase of furniture for the exhibition design; 6.2. search and post text, photo and other materials about the life and work of Zh. I. Alferov; 6.3. Exhibition design. Task 7. Include information about Zh. I. Alferov in the material of the tour of the exhibition "Our Chashnichchina", a walking tour of the city. 7.1. Search and organize information about Zh. I. Alferov; 7.2. add information and edit the text of excursions. Task 8. Publication of a series of informational booklets aimed at popularizing the activities of Zh. Alferova Street. 8.1. Study and selection of materials for inclusion in the booklet; 8.2. Development of the booklet layout; 8.3. Printing of the booklet. |
| 14. | Project rationale | Time puts forward its heroes. These are not necessarily war heroes. In peacetime, heroes can be called people who leave behind, and maybe even in life, something important, something that will be remembered by their descendants. Knowledge of the history of the small homeland, knowledge and memory of their fellow countrymen, their deeds is the duty of everyone. Since ancient times, a Russian person, a Russian soul, being far from his homeland, from his place of residence, openly rejoices when meeting a fellow countryman. What does this word mean, which instantly makes strangers related? Let's turn to Ozhegov's dictionary: "A fellow countryman is a native of the same area as someone else." "Community – belonging by birth to the same locality; association of natives of the same locality." Explanatory dictionary of the Russian language. The explanatory dictionary of the Russian language by S. I. Ozhegov and N. Yu.Shvedov gives the following explanation of the word "countryman":: fellow countryman,- a, m. A native of the same family as someone else. localities. We're with him ~and. In the dictionary of Russian synonyms, the words closest in meaning to the word "countryman" are: fellow tribesman, comrade; fellowcountryman, compatriot, svoezemets, zema, zemelya, odnodozemets o dnozemets, zemlyachok. In this project, I would like to tell you about my fellow countryman, a selfless worker, a person who my city is proud of, as well as about a person who is not a fellow countryman, but who has made a great contribution to the history of my city and country. The chosen topic was motivated not only by interest and respect for the life and work of Zhores Ivanovich Alferov, but also by a desire to learn more about his life history, professional victories and achievements. The name of Zhores Alferov is well-known all over the world, but he is treated in a special way at home. After all, the famous physicist Zhores Ivanovich took his first steps on the road of life on our earth. Here are its roots. Zhores Ivanovich Alferov was born on March 13, 1930 in Vitebsk. His father Ivan Karpovich Alferov, a peasant originally from the Belarusian town of Chashniki, worked as a longshoreman. He fought on the fronts ofthe First World War and rose to the rank of Hussar non-commissioned officer, and in 1917 joined the Bolsheviks. Ivan Alferov met his wife in the 1920s at a border post near the town of Kraisk near Minsk. The future Nobel laureate received his unusual name in honor of the French socialist Jean Jaures. The family moved after new appointments in the service of Ivan Karpovich, who after leaving the reserve worked as a director of various pulp and wood processing plants. The Alferovs lived in Stalingrad, Siberia, the Urals, and Belarus, so Zhores often changed schools. The future famous physicist graduated from the Men's secondary school No. 42 in Minsk in 1947 with a gold medal. He studied for a year at the Belarusian Polytechnic Institute, then entered the second year of the Leningrad Electrotechnical Institute. In 1953, he began working at the Institute of Physics and Technology, and in 1987 he became its head. In 1961, he defended his PhD, and in 1970-Doctor of Physical and Mathematical Sciences. Two years later, he became a professor. The scientist has many high career levels on his account. From 1991 to 2017, he was Vice-president of the Russian Academy of Sciences, and in 1995, he was elected a foreign member of the National Academy of Sciences of Belarus. Zhores Alferov is the author of more than 500 scientific papers and 50 inventions. His research in the field of semiconductor physics, semiconductor and quantum electronics, and technical physics earned him a reputation as a pioneer scientist and marked the beginning of a new scientific school — the physics of semiconductor heterostructures. The first transistors in the USSR, photodiodes, germanium rectifiers — Zhores Alferov had a hand in all this. Not without reason, back in 1972, the scientist was awarded the Lenin Prize — the highest award of the Union for achievements in the field of science. A list of all the high awards and regalia of a scientific luminary, public and political figure would take several pages. The solar panels he developed provided electricity to the Mir space station. Isn't that why his name is immortalized in space? In honor of Zhores Alferov, the asteroid 3884 was named in 1997, and in 2021-the largest Yakut diamond found weighing more than 70 carats. Zhores Alferov and Herbert Kremer were jointly Semiconductor heterostructure warded half of the 2000 Nobel Prize in Physics for the development of semiconductor heterostructures used in high-speed and optoelectronics. The Nobel laureate spent a significant part of his own remuneration on the creation of the International Alferov Foundation for Support of Education and Science. Then he replenished it at the expense of his bonuses and royalties. The purpose of the foundation was to support the scientific research of young scientists, to promote research work. Among the foundation's fellows were students of VSTU, where the famous scientist has been an honorary professor since 2007, and students of Vitebsk Gymnasium No. 1, named after Zhores Alferov since 2019. It is a tradition to celebrate the birthday of the great scientist — March 15 — to hold Alferov readings. The eminent physicist was always happy to come to Belarus and his small homeland in particular, to meet and talk with fellow countrymen. |
| 15. | Activities after the end of the project | After the end of the project Chashnichchina, an exhibition dedicated to Zh. I. Alferov will be created in the exhibition hall of the Nasha Chashnichchina Museum, information about Zh.I. Alferov will be included in the museum's sightseeing tour, used for a walking tour of the city. |
| 16. | Project budget | Production of a bronze plaque in the Belarusian language size 45x45 cm – 300 BYN Production of a granite pedestal 165x40cm. – 1200 BYN Production of a monument-bust of 70 cm. – 3500 BYN. the price includes -sculpting by a sculptor with a photo; - molding; - casting; - grinding; - patina (optional) Earthworks: installation of a sand base under the foundation, sand for construction works, installation of a crushed stone base under the foundation-3000 BYN Installation of the foundation-1500 BYN Installation of the monument-bust – 1500 BYN. Installation of the pedestal on the foundation-1500 BYN. Improvement of the place of installation of the monument-bust – 8000 BYN. Laying of paving slabs around the monument-bust – 6 000 BYN The price includes a monolithic reinforced foundation + facing and laying of granite tiles (2,0*2,3m) Materials: sand, cement, tile glue, crushed stone-2500 BYN Workers ' wages – 7,000 BYN. TOTAL:36 000 BYN. 105 480 $ |

We will be glad to cooperate!